## RetailCo Project Plan DRAFT
RetailCo: Project Plan
Increasing the percentage of MWBE suppliers
Deploying $25M investment in MWBEs via. CDFI
|  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
Sub-project | Phase | Activity | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
MWBE Supplier % | Research | Overall
MWBE Supplier % | Research | Identify Stakeholders (List internal and external stakeholders)
MWBE Supplier % | Research | Conduct Interviews (Interview procurement team and leadership)
MWBE Supplier % | Research | Supplier surveys (Collect feedback from existing suppliers)
MWBE Supplier % | Fact-base | Overall
MWBE Supplier % | Fact-base | Analyze supplier data (Understand current MWBE % and gaps)
MWBE Supplier % | Fact-base | Benchmarking (Compare with competitors and industry)
MWBE Supplier % | Strategy Dev. | Overall
MWBE Supplier % | Strategy Dev. | Define vision (Set MWBE doubling goal)
MWBE Supplier % | Strategy Dev. | Strategic pillars (Create key initiatives (outreach, onboarding))
MWBE Supplier % | Strategy Dev. | Define KPI's (Set success metrics)
MWBE Supplier % | Roll out | Overall
MWBE Supplier % | Roll out | Supplier Onboarding (Develop onboarding process)
MWBE Supplier % | Roll out | Training (Train procurement team)
MWBE Supplier % | Roll out | Launch (Start initiatives)
MWBE Supplier % | Roll out | Monitoring (Track progress and KPIs)
MWBE Investment | Research | Overall
MWBE Investment | Research | Define fund purpose (Clarify objectives of $25M fund)
MWBE Investment | Research | Define financial + social returns
MWBE Investment | Invest. Thesis | Overall
MWBE Investment | Invest. Thesis | Investment criteria (Set eligibility criteria for MWBEs)
MWBE Investment | Invest. Thesis | Impact estimation (Estimate financial and social returns)
MWBE Investment | Fund Options | Overall
MWBE Investment | Fund Options | Research CDFIs (Create long list of options)
MWBE Investment | Fund Options | Evaluation criteria (Define scoring model)
MWBE Investment | Op. Model | Overall
MWBE Investment | Op. Model | Define roles (Assign responsibilities)
MWBE Investment | Op. Model | Governance setup (Create decision-making structure)
MWBE Investment | Op. Model | Reporting (Define tracking & reporting system)
MWBE Investment | Short-list | Overall
MWBE Investment | Short-list | Score CDFI's
MWBE Investment | Short-list | Create Shortlist (Select top candidates)
MWBE Investment | Selection | Overall
MWBE Investment | Selection | Final recommendation (Choose best CDFI partner)